## 1_Dashboard
📊 SEMESTER PROJECT TRACKER
AI-Powered Travel Sentiment & Trend Analytics Platform
PROJECT INFO |  |  | AT A GLANCE
Project Name | AI-Powered Travel Sentiment & Trend Analytics Platform |  | TASKS DONE | TOTAL HOURS LOGGED
Semester | 7th Semester |  | 1 | 5
Start Date | 2026-06-21
Target End Date | 2026-10-21 |  | OPEN BUGS | TASKS LOGGED
Today's Date | 2026-06-22 |  | 0 | 9
Days Remaining | 122
Current Phase | Research & Planning
Overall Progress | 1.875%
PHASE PROGRESS |  |  | MOTIVATION
Phase | Status | Progress | "The secret of getting ahead is getting started." — Mark Twain Focus on consistency, not perfection. One task at a time, one commit at a time.
Research & Planning | In Progress | 15%
Dataset Collection | Not Started | 0%
Data Cleaning & Preprocessing | Not Started | 0%
NLP Sentiment Analysis | Not Started | 0%
Model Training & Evaluation | Not Started | 0%
Dashboard / App Development | Not Started | 0%
Testing & Documentation | Not Started | 0%
Final PPT & Viva Prep | Not Started | 0%
ANALYTICS SNAPSHOT (see 8_Analytics tab for full detail)

## 2_Roadmap
🗺️ MASTER ROADMAP
Break the semester into phases. Update Status — Progress % and the Dashboard update automatically.
Phase | Start Date | End Date | Status | Progress % | Notes
Research & Planning | 21 Jun 2026 | 30 Jun 2026 | In Progress | 15%
Dataset Collection | 01 Jul 2026 | 15 Jul 2026 | Not Started | 0%
Data Cleaning & Preprocessing | 16 Jul 2026 | 31 Jul 2026 | Not Started | 0%
NLP Sentiment Analysis | 01 Aug 2026 | 20 Aug 2026 | Not Started | 0%
Model Training & Evaluation | 21 Aug 2026 | 10 Sep 2026 | Not Started | 0%
Dashboard / App Development | 11 Sep 2026 | 30 Sep 2026 | Not Started | 0%
Testing & Documentation | 01 Oct 2026 | 12 Oct 2026 | Not Started | 0%
Final PPT & Viva Prep | 13 Oct 2026 | 21 Oct 2026 | Not Started | 0%
OVERALL |  |  |  | 1.875%

## 3_Daily_Log
📝 DAILY WORK LOG
Log every work session here. This sheet powers your Dashboard, Weekly Sprints, and Analytics.
Date | Task | Category | Hours | Status | Difficulty | Notes
2026-06-21 | Discussed project idea and finalized concept | Research | 1 | Done | Easy | AI-Powered Travel Sentiment & Trend Analytics Platform
2026-06-21 | Reviewed 9-day work plan (Week 1 PDF) | Documentation | 0.5 | Done | Easy | Understood Day 1–9 tasks for June 22–30
2026-06-21 | Decided folder structure and created it on E: drive | Coding | 0.5 | Done | Easy | data/raw, data/cleaned, notebooks/, src/preprocessing/, src/utils/
2026-06-21 | Created 3 starter files | Coding | 0.5 | Done | Easy | requirements.txt, .gitignore, README.md
2026-06-21 | Installed Git and configured identity | Coding | 0.5 | Done | Easy | Name: Krishna, email: krishnagondaliya034@gmail.com
2026-06-21 | Created GitHub repo and connected local project | Github | 1 | Done | Medium | github.com/Krishnaaa0811/travel-sentiment-analytics
2026-06-21 | Made first commit and pushed to GitHub | Github | 0.5 | Done | Medium | Commit: "Initial project structure with folders, README, gitignore"
2026-06-21 | Created Practice folder separately | Coding | 0.5 | Done | Easy | E:\Practice\01_python_basics\ — outside main repo

## 4_Weekly_Sprints
🏁 WEEKLY SPRINT TRACKER
Set a goal each week, then check real progress. Hours Logged pulls automatically from Daily Log.
Week # | Start Date | End Date | Weekly Goal | Hours Logged | Completion % | Reflection / Notes
1 | 2026-06-21 | 2026-06-30 | Set up project structure, repo, and tracker | 5 | 30% | done
2 | 2026-07-01 | 2026-07-04 |  | 0 | 0%
3 | 2026-07-05 | 2026-07-11 |  | 0 | 0%
4 | 2026-07-12 | 2026-07-18 |  | 0 | 0%
5 | 2026-07-19 | 2026-07-25 |  | 0 | 0%
6 | 2026-07-26 | 2026-08-01 |  | 0 | 0%
7 | 2026-08-02 | 2026-08-08 |  | 0 | 0%
8 | 2026-08-09 | 2026-08-15 |  | 0 | 0%
9 | 2026-08-16 | 2026-08-22 |  | 0 | 0%
10 | 2026-08-23 | 2026-08-29 |  | 0 | 0%
11 | 2026-08-30 | 2026-09-05 |  | 0 | 0%
12 | 2026-09-06 | 2026-09-12 |  | 0 | 0%
13 | 2026-09-13 | 2026-09-19 |  | 0 | 0%
14 | 2026-09-20 | 2026-09-26 |  | 0 | 0%
15 | 2026-09-27 | 2026-10-03 |  | 0 | 0%
16 | 2026-10-04 | 2026-10-10 |  | 0 | 0%
17 | 2026-10-11 | 2026-10-17 |  | 0 | 0%

## 5_Skills_Tracker
🎯 SKILLS PROGRESS TRACKER
Track how each skill is growing across the semester.
Skill | Level Before | Current Level | Target Level | Progress | Notes
Python | Beginner | Beginner | Advanced | 0%
Pandas / NumPy | Beginner | Beginner | Advanced | 0%
NLP (NLTK/spaCy/Transformers) | Beginner | Beginner | Advanced | 0%
REST APIs / Web Scraping | Beginner | Beginner | Intermediate | 0%
Machine Learning | Beginner | Beginner | Advanced | 0%
Streamlit / Dashboarding | Beginner | Beginner | Intermediate | 0%
Power BI / Data Viz | Beginner | Beginner | Intermediate | 0%
Git / GitHub | Intermediate | Beginner | Advanced | 0%
SQL | Beginner | Beginner | Intermediate | 0%
Technical Writing / Docs | Intermediate | Beginner | Advanced | 0%

## 6_Datasets_APIs
🗂️ DATASETS & APIs TRACKER
Keep track of every data source — what it is, its status, and where it stands.
Source | Type | Records / Size | Status | Date Added | Notes

## 7_Bug_Tracker
🐞 BUG & ERROR TRACKER
Every error you hit, logged. Future-you will thank present-you.
Date | Error | Cause | Status | Solution

## 8_GitHub_Tracker
💻 GITHUB TRACKER
Log commits and milestones. Keeps your repo history meaningful for your final report.
Date | Commit Message | Branch | Type | Notes
2026-06-21 | Initial project structure with folders, README, gitignore, and requirements | Main | Milestone | First ever commit — repo live at github.com/Krishnaaa0811/travel-sentiment-analytics

## 9_Analytics
📈 ANALYTICS DASHBOARD
Auto-generated from your Daily Log and Roadmap. Nothing to fill in here — just watch it update.
HOURS LOGGED PER WEEK
Week | Hours | TASK STATUS BREAKDOWN (WITH COUNT)
W1 | 5 | Done | 5
W2 | 0 | In Progress | 0
W3 | 0 | Not Started | 0
W4 | 0 | Blocked | 0
W5 | 0 | HOURS BY CATEGORY
W6 | 0 | Category | Hours
W7 | 0 | Research | 1
W8 | 0 | Coding | 0
W9 | 0 | Data Collection | 0
W10 | 0 | Data Cleaning | 0
W11 | 0 | NLP/ML | 0
W12 | 0 | Dashboard/App | 0
W13 | 0 | Testing | 0
W14 | 0 | Documentation | 0.5
W15 | 0 | GitHub | 2
W16 | 0 | Meeting/Review | 0
W17 | 0 | Other | 0
PHASE PROGRESS %
Phase | Progress
Research & Planning | 15%
Dataset Collection | 0%
Data Cleaning & Preprocessing | 0%
NLP Sentiment Analysis | 0%
Model Training & Evaluation | 0%
Dashboard / App Development | 0%
Testing & Documentation | 0%
Final PPT & Viva Prep | 0%